## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42996 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Thesis report | 2017-09-18 | 2018-05-14 | 238 | 11.9 | 226.1 | 5%
Setup git repo, LaTeK, firmware env. | 2017-09-18 | 2017-09-27 | 9 | 9 | 0 | 100%
Robot generic concept and strategy | 2017-09-18 | 2017-10-08 | 20 | 4 | 16 | 20%
Neural network literature search | 2017-09-18 | 2017-10-28 | 40 | 8 | 32 | 20%
Robot localization visualization | 2017-09-22 | 2017-10-13 | 21 | 12.6 | 8.4 | 60%
Localization sensors functionality + Kalman | 2017-09-22 | 2017-10-07 | 15 | 10.5 | 4.5 | 70%
Tensorflow/neural network experimentation | 2017-10-04 | 2017-10-11 | 7 | 0 | 7 | 0%
Platform PoC bring-up and functionality | 2017-10-11 | 2017-10-14 | 3 | 0 | 3 | 0%
Platform PoC neural network integration | 2017-10-13 | 2017-10-18 | 5 | 0 | 5 | 0%
Platform PoC test field setup | 2017-10-18 | 2017-10-20 | 2 | 0 | 2 | 0%
Platform PoC network training and refinement | 2017-10-20 | 2017-11-03 | 14 | 0 | 14 | 0%
Project proposal and PoC (hopefully) | 2017-11-06 | 2017-11-07 | 1 | 0 | 1 | 0%
Platform refined concept and strategy (need rules) | 2017-11-07 | 2017-11-10 | 3 | 0 | 3 | 0%
Platform design modeling and system block diagram draft | 2017-11-07 | 2017-11-10 | 3 | 0 | 3 | 0%
Platform design review | 2017-11-10 | 2017-11-11 | 1 | 0 | 1 | 0%
Platform design revision + order parts (pending review) | 2017-11-11 | 2017-11-15 | 4 | 0 | 4 | 0%
Platform design review | 2017-11-15 | 2017-11-16 | 1 | 0 | 1 | 0%
Platform part fabrication and assembly | 2017-11-16 | 2017-11-23 | 7 | 0 | 7 | 0%
Platform bring-up and functionality | 2017-11-23 | 2017-11-26 | 3 | 0 | 3 | 0%
Platform network training and refinement | 2017-11-26 | 2017-12-01 | 5 | 0 | 5 | 0%
Finals | 2017-12-02 | 2017-12-06 | 4 | 0 | 4 | 0%
Robot refined concept and strategy | 2017-12-07 | 2017-12-17 | 10 | 0 | 10 | 0%
Robot design modeling and system block diagram | 2017-12-07 | 2018-01-01 | 25 | 0 | 25 | 0%
Robot design review + order parts (pending review) | 2018-01-02 | 2018-01-03 | 1 | 0 | 1 | 0%
Robot part fabrication and assembly | 2018-01-08 | 2018-01-15 | 7 | 0 | 7 | 0%
Robot bring-up and functionality | 2018-01-12 | 2018-01-26 | 14 | 0 | 14 | 0%
Robot network training and refinement | 2018-01-26 | 2018-04-13 | 77 | 0 | 77 | 0%
Finals + Spring break | 2018-03-19 | 2018-04-02 | 14 | 0 | 14 | 0%
Roborodentia | 2018-04-13 | 2018-04-14 | 1 | 0 | 1 | 0%
Improvements | 2018-04-15 | 2018-04-29 | 14 | 0 | 14 | 0%
Thesis oral defense prep | 2018-05-01 | 2018-05-14 | 13 | 0 | 13 | 0%
Expo presentation work | 2018-05-14 | 2018-05-28 | 14 | 0 | 14 | 0%
Thesis oral defense dry run | 2018-05-14 | 2018-05-15 | 1 | 0 | 1 | 0%
Thesis oral defense | 2018-05-21 | 2018-05-22 | 1 | 0 | 1 | 0%
Project expo | 2018-05-28 | 2018-05-29 | 1 | 0 | 1 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.